## Slide 1
NOAA
National Environmental Satellite, Data, and Information Service
Pam Sullivan, Director of GEO Observations
GeoXO Program Update
NOAA’s Satellite Applications Symposium Series: Water
July 29, 2024

## Slide 2
  On May 20th, NOAA/NASA announced the selection of BAE Systems to develop the GeoXO OCX instrument!
Celebratory Pie!

## Slide 3
To be developed by BAE Systems
To be developed by L3Harris
To be developed by BAE Systems
To be developed by BAE Systems

## Slide 4: Lockheed Martin Selected to develop GeoXO Spacecraft

## Slide 5
GeoXO Recent Progress
Systems Requirements Review (SRR) completed Aug 2022
Program officially approved by DOC Deputy Secretary at Milestone 2/3 Dec 2022
Implementation has begun with selection of developers:
  L3Harris for Imager (Mar 2023)
    SRR completed Aug 2023
  BAE for Sounder (Sep 2023)
    SRR completed July 2024
  BAE for Atmo. Composition sensor (May 2024)
  BAE for Ocean Color sensor (May 2024)
  Lockheed Martin for Spacecraft (June 2024)
Final instrument selection will be Lightning Mapper planned Aug 2024
GeoXO logos added to GOES-R store on LandsEnd:
https://business.landsend.com/store/goes-r_program/

## Slide 6: Key Near Term Milestones
Element | Actual/Target Announcement | Actual/Target Kickoff | Actual/Target SRR/SDR
GXI | Mar 2023 | Apr 2023 | Aug 2023
GXS | Sep 2023 | Mar 2024 | Jul 2024
LMX | Aug 2024 | Oct 2024 | Mar 2025
OCX | May 2024 | Aug 2024 | Oct/Nov 2024
ACX | May 2024 | Aug 2024 | Oct/Nov 2024
Spacecraft | June 2024 | Aug 2024 | Nov 2024
MDR/KDP-B Event | Target Date
MDR Dry Run | Oct 22-23
MDR Review Readiness | Nov 8
MDR Dress Rehearsal | Nov 19-21
MDR Review | Dec 10-12
KDP-B APMC | Feb 19

## Slide 7: Program Advocacy is Critical Now
Key activity right now is to justify GeoXO budget with Congress
  FY24 enacted budget was lower than President’s budget ($285M vs PB $417M), requiring us to delay some activities
FY25 President’s budget is $798M
  House ‘mark’ is $150M
  Senate ‘mark’ is $625M
  Senate bill includes the following language:
Program priorities in response to cuts are:
  Continuity of Imager observations
  Retaining all instruments
  Delay launches if needed
Program and Congressional priorities not aligned

## Slide 8: What the Future Holds
Replanning program to fit within enacted FY24 budget, and developing options in response to potential FY25 scenarios, assuming FY26 & out is per Milestone 2/3 plan
Working to justify GeoXO budget with Congress
  Documenting impacts of budget cuts
Continuing program awareness and advocacy efforts with Congress and external user groups
  GeoXO ‘all interested’ briefings to Hill this summer
  GeoXO Road Shows to visit users in the field
  Re-engaging participants from 2020 GeoXO workshops
  Initiated quarterly constituent briefings
  Continuing economic value studies
Plan to submit Congressional Baseline Report Sep 2024
  Earlier than usual to indicate readiness to baseline

## Slide 9
GeoXO Timeline
MS0
MS1
KDP
A
MCR
Form.
Auth.
NOSC
Endorses
Observation
Set
SRR
KDP
dA
MS2/3
(DOC Baseline)
User Reqts
Working
Group
Convened
MDR
KDP
B
FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33
PDR
KDP
C
CDR
SIR
KDP
D
ORR
KDP
E
Congressional Baseline
GeoXO-I1
Launch
Pre-formulation
Formulation
Implementation
Ops
We are here
Contract
Awards
Ocean Color: BAE Systems
Spacecraft: Lockheed Martin
- Lightning Mapper: target award August 2024
Implementation contracts:
Imager: L3Harris
Sounder: BAE Systems
Atmo. Comp.: BAE Systems